IMIS Revamp Loading Protection and Duplicate-Action Prevention

Deeper implementation study, rollout plan, QA strategy, and effort estimate

| Field | Detail |
| --- | --- |
| Audience | Team Leads, PM, Developers, QA, and project stakeholders |
| Prepared for | BaseIMIS / IMIS Revamp team |
| Prepared on | 26 June 2026 |
| Workspace reviewed | C:\xampp\htdocs\lang_web_app |
| Related Jira | BASEIMIS-14 - Implement reusable loading states and duplicate-action prevention across IMIS Revamp |

Recommended move Start with a reusable action-state foundation, not a blanket full-screen loader after every click. Protect valid form submissions and state-changing AJAX actions first; keep navigation, filter toggles, cancel/back actions, map tools, and modal open/close interactions responsive unless they trigger long-running work.

# 1. Executive decision

The goal is not simply to show a loading screen. The real goal is to prevent duplicate writes, reduce accidental repeated submissions, and give users clear feedback when the system is processing an action. A blanket loader after every button would make the application feel slower and can block harmless actions such as filters, navigation, tabs, close buttons, and map tools.

The best path is a hybrid implementation: button-level lock by default, optional full-page overlay for long-running or sensitive flows, and backend duplicate protection for critical records.

# 2. Current code evidence

| Area | Current finding | Implementation meaning |
| --- | --- | --- |
| Shared dashboard layout | resources/views/layouts/dashboard.blade.php already renders a .loading-overlay inside the content section. | Dashboard pages can reuse one central overlay, but the overlay should be controlled predictably. |
| Shared CSS | public/css/style.css already defines .loading-overlay and .loading-overlay.is-active. | Styling exists, but it needs state-safe behavior and button-level states. |
| Shared JS | public/js/functions.js has displayAjaxLoader(), removeAjaxLoader(), exportToCsv(), and preventMultipleSubmit(). | The primitives exist but are incomplete. display/remove use toggle, and preventMultipleSubmit is not wired globally. |
| Shared submit footer | resources/views/layouts/partial-form.blade.php renders many create/edit footers with Back to List and Save. | Highest-leverage place to add safe default submit behavior and data attributes. |
| Custom maps layout | resources/views/maps/index.blade.php defines its own displayAjaxLoader/removeAjaxLoader using .ajax-modal. | Map interactions need a separate phase; they should not inherit a dashboard full-page lock blindly. |
| Sewer approval modal | resources/views/sewer-connection/approve.blade.php performs a state-changing GET AJAX request on Yes. | This is a priority duplicate-action target and should be migrated toward a mutation method and button lock. |
| FSM application create | resources/views/fsm/applications/create.blade.php calls displayAjaxLoader before AJAX, but the error path does not remove it. | Loader finalization should be centralized through complete/finally blocks to avoid stuck UI. |

# 3. Current inventory snapshot

| Metric from current workspace scan | Count | Reading |
| --- | --- | --- |
| Blade forms detected in resources/views and local JS snippets | 81 | Enough surface area to justify shared handling instead of page-by-page one-offs. |
| Button elements detected | 203 | Too broad for blanket loading. Many are navigation, reset, map, modal, or UI toggles. |
| Submit controls detected | 93 | Primary starting target for duplicate form submission protection. |
| jQuery AJAX calls detected | 79 | Needs an opt-in action wrapper and phased migration, especially for mutations. |
| fetch calls detected | 8 | Small enough to review manually after the main jQuery path. |
| prevent-multiple-submits references | 6 | Shows the intent exists but is not consistently applied. |
| displayAjaxLoader calls | 58 | Loader is used, but not standardized. |
| removeAjaxLoader calls | 69 | Asymmetric counts suggest mixed flows, comments, local helpers, and possible stuck/extra remove paths. |

# 4. What should and should not show loading

| Control type | Default behavior | Reason |
| --- | --- | --- |
| Create, Save, Update, Delete, Approve, Assign, Import, Generate | Disable clicked action and show spinner text. Use overlay only for long or sensitive work. | These can create duplicate writes or inconsistent states. |
| AJAX actions that mutate server state | Disable initiating control until success/error completes. | Prevents repeated POST/PATCH/DELETE or state-changing GET calls. |
| CSV/PDF/export generation | Use overlay or clear action feedback if generation takes more than one second. | Users need feedback while file generation or server work happens. |
| Back to List, Cancel, Close modal, No | No loading lock. | These are escape paths and should remain responsive. |
| Filter, Reset, Show/Hide Filter, tab/collapse controls | Usually no full overlay. Button-level feedback only if server reload is slow. | Blocking the full page for light filtering will feel clumsy. |
| Map pan/zoom/draw/select tools | No global dashboard overlay. Use map-specific loader only for server query/report actions. | Map UI must stay interactive; map workflows already have custom loader code. |

# 5. Recommended implementation architecture

## 5.1 Shared action-state module

Create one shared frontend module in public/js/functions.js or a new public/js/action-state.js loaded by dashboard/layers/maps as appropriate. The module should expose clear APIs:

startAction(element, options) - lock the clicked button/link and optionally show overlay.

finishAction(element) - restore button text, disabled state, aria-busy, and overlay state.

withActionState(element, promiseOrCallback, options) - run AJAX/fetch safely and always restore on success, validation error, network error, or thrown exception.

showPageLoader(message) and hidePageLoader() - use classList.add/remove, not toggle.

isActionInProgress(element) - prevent duplicate handling if a user double-clicks before disabled state applies.

## 5.2 Attribute-driven policy

Use data attributes so teams can opt in/out without rewriting every page.

| Attribute | Meaning | Example use |
| --- | --- | --- |
| data-loading="button" | Disable only the clicked action and show spinner/text. | Default for form submits and modal confirm buttons. |
| data-loading="overlay" | Disable the action and show full-screen overlay. | Long-running imports, exports, report generation, heavy save flows. |
| data-loading="none" | Explicit opt-out. | Back, cancel, close, reset, map draw controls. |
| data-loading-message="Saving..." | Custom message shown in overlay or button text. | Save Application, Import Translation, Generate PDF. |
| data-allow-multiple="true" | Permit repeated interaction. | Map zoom, drawing tools, tab/collapse controls. |

## 5.3 Safe loader behavior

Replace toggle-based loader behavior with explicit add/remove. Current toggle behavior can hide the loader when two operations overlap or leave it visible after an error.

Use request counting for global overlay if multiple AJAX calls can run at the same time.

Always remove loader in jQuery complete handlers and fetch finally blocks.

Do not disable the whole form until client-side validation has passed.

Set aria-busy="true" and restore focus/labels so the behavior remains accessible.

# 6. Practical rollout plan

| Phase | Scope | Files / modules | Outcome |
| --- | --- | --- | --- |
| Phase 0 - confirm policy | Agree which actions get button lock, overlay, or no lock. | Team review of this document and BASEIMIS-14. | Prevents accidental over-blocking of the UI. |
| Phase 1 - foundation | Implement shared action-state helper, safe overlay add/remove, CSS for button spinner, and data attributes. | public/js/functions.js or public/js/action-state.js; public/css/style.css; layouts/dashboard.blade.php; layouts/layers.blade.php if needed. | Reusable foundation with minimal page edits. |
| Phase 2 - form submissions | Apply delegated submit protection to create/edit forms and partial-form submit footer. | resources/views/layouts/partial-form.blade.php and form pages using conventional Laravel submits. | Most duplicate form submissions controlled. |
| Phase 3 - high-risk AJAX | Wrap mutation AJAX and modal confirm actions. | sewer-connection/approve.blade.php; fsm/applications/create.blade.php; fsm/applications/edit.blade.php; fsm/emptying/create.blade.php; import/generate flows. | Repeated clicks on state-changing operations are blocked. |
| Phase 4 - backend integrity | Add server-side duplicate/state guards for critical flows. | ApplicationController, EmptyingController, SludgeCollectionController, SewerConnectionController, import/generate endpoints. | Frontend protection is backed by durable server safety. |
| Phase 5 - maps/layers | Standardize map-specific loaders without blocking pan/zoom/draw controls. | resources/views/maps/index.blade.php; layer-info and public-health partial forms. | Map UX stays responsive while long server queries are clear. |
| Phase 6 - QA hardening | Regression test forms, AJAX errors, exports, validation, and browser back behavior. | QA test matrix below. | Release-ready confidence. |

# 7. Suggested first move

Do not start by editing every button. Start by creating the shared helper and replacing displayAjaxLoader/removeAjaxLoader toggle behavior with explicit add/remove.

Add delegated form-submit protection that runs only for valid form submissions and skips forms/buttons marked data-loading="none" or data-allow-multiple="true".

Patch the known stuck-loader case in FSM application create/edit by moving removeAjaxLoader behavior to complete/finally.

Patch the sewer approval modal confirm button because it is a state-changing action exposed to repeated clicks.

Review server-side duplicate guards for Application, Emptying, Sludge Collection, and Sewer Connection approval flows.

# 8. Developer implementation checklist

Create a small action-state helper and load it once in shared layouts.

Add CSS for .is-loading buttons, spinner icon spacing, disabled cursor, and overlay messages.

Set submit buttons generated by partial-form.blade.php to data-loading="button" by default.

Use data-loading="none" for Back to List, Cancel, Close, Reset, Show/Hide Filter, and map tool buttons.

Wrap jQuery AJAX actions with beforeSend/complete or the shared withActionState helper.

Wrap fetch actions with try/catch/finally and the same action-state helper.

Avoid global ajaxStart/ajaxStop for all AJAX because DataTables/select2/background requests can cause unwanted full-page flicker.

Convert state-changing GET endpoints to POST/PATCH where feasible, or at minimum lock the initiating button and add server-side state checks.

Write a short developer note showing data-loading usage examples.

# 9. Backend safeguards

Frontend locking reduces accidental repeats, but it does not guarantee integrity. Users can refresh, browser retry, double-submit from multiple tabs, or call endpoints directly. Critical operations need backend checks.

| Flow | Risk if only frontend is fixed | Backend safeguard |
| --- | --- | --- |
| FSM application create | Duplicate ongoing applications for one address/containment if parallel requests slip through. | Validate existing active application inside transaction or unique/state constraint. |
| Emptying create/update | Duplicate service record or wrong containment status transition. | State guard plus transaction around emptying and related containment/application updates. |
| Sludge collection | Duplicate collection/event rows and inconsistent volume/reporting. | Idempotent create rules or uniqueness on source event where business rules allow. |
| Sewer connection approval | Repeated approval can remove/update related containment state multiple times. | Use POST/PATCH, check current state before update, and return already-processed response safely. |
| Import/generate translation | Repeated imports/generation can duplicate or overwrite in unexpected order. | Job/status guard, idempotent update, or confirmation around overwrite behavior. |

# 10. QA strategy

| QA area | Scenarios to test | Expected result |
| --- | --- | --- |
| Normal form submit | Click Save repeatedly on create/edit forms. | Only one request is submitted; button shows loading and restores only if validation blocks submit or response returns. |
| Validation errors | Submit invalid form, including required fields and server validation errors. | User can correct and resubmit; button is not permanently disabled. |
| AJAX success | Use BIN/address lookup, sewer approve, import/generate, and export flows. | Action control locks during request and restores or redirects after completion. |
| AJAX error | Force network/server error or invalid response. | Loader is removed, error is visible, and user can retry safely. |
| Navigation and cancel | Back to List, Cancel, modal No/Close, Show/Hide Filter. | No unnecessary loading screen; action remains responsive. |
| Maps | Pan/zoom/draw, then run server-side map reports. | Map tools remain interactive; loader appears only for long server/report operations. |
| Accessibility | Keyboard-submit forms and screen reader semantics. | Disabled/loading state is announced using aria-busy or clear text; focus is not trapped unnecessarily. |
| Concurrency | Double-click quickly, submit from two tabs, refresh during request. | Frontend prevents most repeats; backend handles unavoidable repeats safely. |

# 11. Effort estimate

| Scope option | Engineering estimate | QA estimate | When to choose |
| --- | --- | --- | --- |
| Minimum frontend-only pass | 3-5 engineer days | 1-2 QA days | Use only if the team needs quick visible duplicate-click protection on common forms. |
| Recommended complete pass | 7.5-12 engineer days | 2-3 QA days | Best fit for production: shared helper, form protection, AJAX fixes, backend guards, and QA matrix. |
| Deep exhaustive pass | 12-18 engineer days | 4-5 QA days | Use if the team wants to normalize maps, DataTables, every export, and all edge modules in the same release. |

Planning estimate: 10 engineer days and 3 QA days, with an expected calendar duration of about 2-3 working weeks when handled by one primary engineer and one QA, with PM/lead review at phase gates.

# 12. Release recommendation

Release this as a small product-quality improvement, not a visual-only loading ticket. The release should be accepted only when duplicate-action prevention works for real form submissions and high-risk AJAX paths, and when QA confirms users are not blocked from navigation or corrections.

| Week | Recommended work | Exit criteria |
| --- | --- | --- |
| Week 1 | Foundation helper, CSS, shared submit handling, loader toggle replacement. | Common create/edit forms have working button-level loading with no validation deadlocks. |
| Week 2 | High-risk AJAX and backend safeguards. | Known mutation flows cannot be repeatedly clicked into duplicate states. |
| Week 3 buffer | Maps/layers, regression fixes, QA retesting, release notes. | No stuck loaders, no over-blocked controls, and no duplicate-action regressions. |

# 13. Acceptance criteria for Jira / release

A reusable loading/action-state helper is available and documented.

Submit buttons on create/edit forms disable only after a valid submission starts.

Long-running operations can show a full-page overlay with a clear message.

Cancel, back, reset, close, tab, collapse, and map interaction controls are not blocked by default.

AJAX/fetch actions always restore UI state on success, validation error, network error, and thrown exceptions.

At least the identified high-risk flows have backend duplicate/state guards.

QA has executed normal, validation, error, retry, double-click, and browser-back scenarios.

No known flow leaves a loader stuck or a button permanently disabled.

# 14. Risks and controls

| Risk | Why it matters | Control |
| --- | --- | --- |
| Over-blocking UI | A loader after every button can make the app feel frozen and frustrate users. | Use attribute policy and exclude non-mutating controls. |
| Stuck loader | Existing toggle/remove patterns can leave overlays visible after errors. | Use explicit add/remove and finally/complete cleanup. |
| False safety | Frontend locks cannot prevent duplicate server requests from tabs or direct calls. | Add backend transactions/state checks for critical operations. |
| Map workflow regression | Map page has many custom interactions and custom loader modal. | Handle maps in a separate phase with map-specific QA. |
| DataTables/select2 flicker | Global ajaxStart/ajaxStop can trigger loaders during background requests. | Avoid blanket global AJAX overlay; wrap only user-initiated actions. |

# 15. Final recommendation

Move forward with the recommended complete pass. The minimum frontend pass is tempting, but it leaves the real duplicate-data risk unresolved. The recommended complete pass is still manageable in a 2-3 week window and gives PM, team leads, developers, and QA a clean implementation contract.

# Appendix A. Evidence notes

The shared loader exists in dashboard layout and style.css, but helper functions currently use classList.toggle instead of explicit state.

The shared partial form footer has a natural place to add data-loading defaults for Save without affecting Back to List.

The maps page is a special case with a local ajax-modal loader and should not be normalized blindly.

The sewer approval modal is a priority because the user can repeatedly click Yes while a state-changing GET request is in flight.

The FSM application create page shows why complete/finally cleanup matters: success removes the loader, but the error branch does not call removeAjaxLoader in the inspected snippet.